## BurndownChart
| Punten | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3
Taak | geschat | wk39 | wk40 | wk41 | wk42
Create DoD | 2 | 2
Setup GitHub Enviroment | 3 | 3
Burndown | 2 |  | 2
Setup automated testing workflows | 6 | 3 |  |  | x
Setup Visual Studio Project | 3 | 3
US01 - Implement user authentication
Wireframe Home page | 3 |  | 3
Wireframes Login & Register page | 2 |  | 2
Frontend Login & Register page | 4 |  | x
Backend Login & Register page | 2 |  | x
Backend User object | 6 |  | 6
ERD User | 2 |  | 2
Frontend Home page | 3 |  | x
US02 - Implement election management
Wireframe Create Election page | 2 |  |  | x
Frontend Create Election page | 4 |  |  | x
Backend Election object | 3 |  |  | x
Backend Create Election page | 4 |  |  | x
ERD Election | 1 |  |  | x
US03 - Implement Political Parties
ERD Party object | 1 |  |  | x
Backend Party object | 4 |  |  | x
Backend Party Mutation page | 4 |  |  | x
Wireframe Party Mutation page | 2 |  |  | x
Frontend Party Mutation page | 3 |  |  | x
US04 - Link User to parties
Backend Party Member object | 1 |  |  | x
Backend Party Leader object | 1 |  |  | x
Backend Party Member Mutation page | 3 |  |  | x
Frontend Party Member Mutation page | 3 |  |  | x
Wireframe Party Member Mutation page | 2 |  |  | x
US05 - Select Candidate per election
Wireframe Select Candidate page | 2 |  |  | x
Backend Select Candidate page | 3 |  |  | x
Frontend Select Candidate page | 3 |  |  | x
US06 - Determine candidate order
Frontend Select Candidate page(Order) | 3 |  |  |  | x
Backend Select Candidate page(Order) | 3 |  |  |  | x
Backend Electable Member object | 2 |  |  |  | x
ERD Electable Member | 2 |  |  |  | x
US07 - Implement eligibility
Backend Eligible Voter object | 1 |  | x
US08 - Schedule elections
Wireframe Schedule Elections page | 2 |  |  | x
Frontend Schedule Elections page | 3 |  |  |  | x
Backend Schedule Elections page | 3 |  |  |  | x
US09 - Ensure elligible voters can vote only once
Wireframe Vote On Elections page | 3 |  | 3
Frontend Vote On Elections page | 5 |  |  |  | x
Backend Vote On Elections page | 4 |  |  |  | x
US10 - Implement election information(gov)
Wireframe Election Information page | 2 |  |  | x
Frontend Election Information page | 6 |  |  |  | x
Backend Election Information page | 3 |  |  |  | x
US11 - Implement invitations
Backend Send Invitations To Eligible Voters page | 3 |  |  | x
US12 - Publish results
Wireframe Election Results page | 2 |  |  | x
Frontend Election Results page | 4 |  |  |  | x
Backend Election Results page | 3 |  |  |  | x
US13 - Party Information
Wireframe Party Information page | 1 |  | 1
Frontend Party Information page | 3 |  |  |  | x
Backend Party Information page | 2 |  |  |  | x
Nog doen | 144 | 133 | 115 | 115 | 115
Planning | 144 | 108 | 72 | 36 | 0